## Assignment 3
Task/Contribution(~30 words) | Contribution type | Planning Date | Contributor | Status | Actual Completion Date | Extra notes
First meeeting discussion | Discussion | 2023-05-01 | EVERYONE | DONE | 2023-05-01 | We had a 1 hour meeting to read the assignment specifications together and agreed to do all the work simultaneously by having meetings for the rest of the week
Develop the Game: Req 1 | Coding | 2023-05-08 | EVERYONE | DONE | 2023-05-09
Develop the Game: Req 2 | Coding | 2023-05-09 | EVERYONE | DONE | 2023-05-10
Develop the Game: Req 3 | Coding | 2023-05-10 | EVERYONE | DONE | 2023-05-11
Develop the Game: Req 4 | Coding | 2023-05-11 | EVERYONE | DONE | 2023-05-12
Develop the Game: Req 5 | Coding | 2023-05-12 | EVERYONE | DONE | 2023-05-13
Update UML: Req 1 | UML Diagram | 2023-05-15 | EVERYONE | DONE | 2023-05-16
Update UML: Req 2 | UML Diagram | 2023-05-15 | EVERYONE | DONE | 2023-05-16
Update UML: Req 3 | UML Diagram | 2023-05-15 | EVERYONE | DONE | 2023-05-16
Update UML: Req 4 | UML Diagram | 2023-05-15 | EVERYONE | DONE | 2023-05-16
Update UML: Req 5 | UML Diagram | 2023-05-15 | EVERYONE | DONE | 2023-05-16
Update Design Rationale | Design Rationale | 2023-05-16 | EVERYONE | DONE | 2023-05-18

## Assignment 2
Task/Contribution(~30 words) | Contribution type | Planning Date | Contributor | Status | Actual Completion Date | Extra notes
First meeeting discussion | Discussion | 2023-04-16 | EVERYONE | DONE | 2023-04-16 | We had a 1 hour meeting to read the assignment specifications together and agreed to do all the work simultaneously by having meetings for the rest of the week
Develop the Game: Req 1 | Coding | 2023-04-17 | EVERYONE | DONE | 2023-04-29
Develop the Game: Req 2 | Coding | 2023-04-17 | EVERYONE | DONE | 2023-04-29
Develop the Game: Req 3 | Coding | 2023-04-17 | EVERYONE | DONE | 2023-04-29
Develop the Game: Req 4 | Coding | 2023-04-17 | EVERYONE | DONE | 2023-04-29
Develop the Game: Req 5 | Coding | 2023-04-17 | EVERYONE | DONE | 2023-04-29
Update UML: Req 1 | UML Diagram | 2023-04-29 | EVERYONE | DONE | 2023-04-30
Update UML: Req 2 | UML Diagram | 2023-04-29 | EVERYONE | DONE | 2023-04-30
Update UML: Req 3 | UML Diagram | 2023-04-29 | EVERYONE | DONE | 2023-04-30
Update UML: Req 4 | UML Diagram | 2023-04-29 | EVERYONE | DONE | 2023-04-30
Update UML: Req 5 | UML Diagram | 2023-04-29 | EVERYONE | DONE | 2023-04-30
Sequence Diagram: Req 1 | Sequence Diagram | 2023-04-30 | EVERYONE | DONE | 2023-05-01
Sequence Diagram: Req 2 | Sequence Diagram | 2023-04-30 | EVERYONE | DONE | 2023-05-01
Sequence Diagram: Req 3 | Sequence Diagram | 2023-04-30 | EVERYONE | DONE | 2023-05-01
Sequence Diagram: Req 4 | Sequence Diagram | 2023-04-30 | EVERYONE | DONE | 2023-05-01
Sequence Diagram: Req 5 | Sequence Diagram | 2023-04-30 | EVERYONE | DONE | 2023-05-01
Update Design Rationale | Design Rationale | 2023-05-01 | EVERYONE | DONE | 2023-05-02

## Assignment 1
Task/Contribution(~30 words) | Contribution type | Planning Date | Contributor | Status | Actual Completion Date | Extra notes
First meeeting discussion | Discussion | 2023-04-04 | EVERYONE | DONE | 2023-04-04 | We had a 1 hour meeting to read the assignment specifications together and agreed to do all the work simultaneously by having meetings for the rest of the week
List out all actors, items, and grounds in the whole assignment | Brainstorm | 2023-04-04 | EVERYONE | DONE | 2023-04-04
Requirement 1: Environments | UML diagram | 2023-04-05 | EVERYONE | DONE | 2023-04-06
Requirement 1: Enemies | UML diagram | 2023-04-05 | EVERYONE | DONE | 2023-04-06
Requirement 1: Weapons | UML diagram | 2023-04-05 | EVERYONE | DONE | 2023-04-06
Requirement 2: Enemies | UML diagram | 2023-04-05 | EVERYONE | DONE | 2023-04-08
Requirement 2: Trader | UML diagram | 2023-04-05 | EVERYONE | DONE | 2023-04-08
Requirement 2: Weapons | UML diagram | 2023-04-05 | EVERYONE | DONE | 2023-04-08
Requirement 3: Flask of Crimson Tears | UML diagram | 2023-04-06 | EVERYONE | DONE | 2023-04-08
Requirement 3: Site of Lost Grace | UML diagram | 2023-04-06 | EVERYONE | DONE | 2023-04-08
Requirement 3: Game Reset | UML diagram | 2023-04-06 | EVERYONE | DONE | 2023-04-08
Requirement 3: Runes | UML diagram | 2023-04-06 | EVERYONE | DONE | 2023-04-08
Requirement 4: The Player | UML diagram | 2023-04-07 | EVERYONE | DONE | 2023-04-08
Requirement 4: Classes/Combat Archetypes | UML diagram | 2023-04-07 | EVERYONE | DONE | 2023-04-08
Requirement 4: Weapons | UML diagram | 2023-04-07 | EVERYONE | DONE | 2023-04-08
Requirement 5: Enemies | UML diagram | 2023-04-08 | EVERYONE | DONE | 2023-04-11
Requirement 5: Weapons | UML diagram | 2023-04-08 | EVERYONE | DONE | 2023-04-11
Design Rationale | Design Rationale | 2023-04-12 | EVERYONE | DONE | 2023-04-14